## Plan and Burndown
User Story | T Shirt Size | Task | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Total Story Time Remaining | Day | Work Left (Hours)
Story 1 | M | Task 1.1 | Day 1: 4 | 16 | 1 | 116
|  | Task 1.2 | Day 1: 4 |  | 2
|  | Task 1.3 | Day 1: 8 |  | 3
Story 2 | S | Task 2.1 | Day 1: 4 | 8 | 4
|  | Task 2.2 | Day 1: 4 |  | 5
Story 3 | M | Task 3.1 | Day 1: 4 | 16 | 6 | 0
|  | Task 3.2 | Day 1: 4
|  | Task 3.3 | Day 1: 8
Story 4 | S | Task 4.1 | Day 1: 4 | 4
Story 5 | M | Task 5.1 | Day 1: 4 | 10
|  | Task 5.2 | Day 1: 2
|  | Task 5.3 | Day 1: 4
Story 6 | S | Task 6.1 | Day 1: 2 | 6
|  | Task 6.2 | Day 1: 4
Story 7 | L | Task 7.1 | Day 1: 4 | 34
|  | Task 7.2 | Day 1: 4
|  | Task 7.3 | Day 1: 2
|  | Task 7.4 | Day 1: 4
|  | Task 7.5 | Day 1: 4
|  | Task 7.6 | Day 1: 4
|  | Task 7.7 | Day 1: 8
|  | Task 7.8 | Day 1: 4
Story 8 | M | Task 8.1 | Day 1: 4 | 10
|  | Task 8.2 | Day 1: 2
|  | Task 8.3 | Day 1: 4
Story 9 | M | Task 9.1 | Day 1: 2 | 12
|  | Task 9.2 | Day 1: 2
|  | Task 9.3 | Day 1: 4
|  | Task 9.4 | Day 1: 4

## Backlog
User Story | Tasks | Time
1 Side view of runway | 1.1 Implement bitmap drawing system | 4
| 1.2 draw functions | 4
| 1.3 layering additional information on diagram | 8
2 Have key information for all UK airports | 2.1 Collect data from ead.eurocontrol.int | 4
| 2.2 Convert data to XML format | 4
3 Top down view of runway | 3.1 Implement bitmap drawing system | 4
| 3.2 draw functions | 4
| 3.3 layering additional information on diagram | 8
4 View of the original runway values | 4.1 display runway values (update on change) | 4
5 Select different runways and thresholds | 5.1 Adjust data model on selection change | 4
| 5.2 Update graphical representation of runway | 2
| 5.3 Update view of runway values | 4
6 Have a display of cleared and graded areas | 6.1 calculate cleared and graded areas from runway values | 2
| 6.2 draw clear and graded areas to top down view panel | 4
7 Intuitive GUI | 7.1 Design User Interface | 4
| 7.2 Implement view class | 4
| 7.3 Implement main window (class) | 2
| 7.4 Implement (top down&side) view panel (class) | 4
| 7.5 Add calculations breakdown panel (class) | 4
| 7.6 implement runway info selection panel (class) | 4
| 7.7 Implement create object window (class) | 8
| 7.8 Implement control bar (class) | 4
8 Automatically rotate views of runway | 8.1 Implement a button and vairables into the display panel and controller | 4
| 8.2 Convert runway bearings into angle value in radians | 2
| 8.3 Write frame so image does not extend to the edges of its panel | 4
9 Import/export airport information to/from XML | 9.1 Develop XML file read layer | 2
| 9.2 Convert XML data to data structure for processing | 2
| 9.3 Reflect changes in airport data structure back to XML | 4
| 9.4 Develop XML file write layer so that changes persist | 4